POVIEW.AI Project Plan and Risk Register

Timeline: April 2025 - March 2026

TRL 3 (Completed) – Concept Validation

- Objective: Test and validate the initial concept using OpenAI's general model with sample client data.

- Key Tasks: Process data samples from Product Documents, Marketing Collateral, and Client Statements.

- Dependencies: N/A (Initial Phase).

TRL 4 (April 2025 - May 2025) – Dataset Acquisition and Model Architecture

- Objective: Acquire a full training dataset, cleanse it, and implement the model architecture.

- Key Tasks:

  - Data acquisition and cleansing

  - Model architecture selection and implementation

  - Initial UX scoping and design

- Dependencies:

  - Completion of TRL 3 validation phase

  - Full acquisition of the training dataset

- Risks: Potential delays in data acquisition; challenges in finding suitable resources.

TRL 5 (June 2025 - October 2025) – Model Training and UX Development

- Objective: Train the model, conduct quality assurance, and refine the UX.

- Key Tasks:

  - Model training with curated datasets

  - Evaluation and optimization of content governance

  - Initial development of UX/application based on model insights

- Dependencies:

  - Successful completion of TRL 4 dataset acquisition and model architecture

- Risks: Resource availability; significant issues during beta testing; UX adjustments.

TRL 6 (November 2025 - March 2026) – Final Testing and Beta Phase

- Objective: Conduct legal and governance checks, beta testing, and finalize UX.

- Key Tasks:

  - Legal and regulatory compliance validation

  - Beta testing with partner feedback loops

  - Final UX and application development

- Dependencies:

  - Completion of TRL 5 model training and initial UX

- Risks: Compliance challenges; delays or issues with beta tester feedback; resource availability.

Initial Commercial Launch (March 2026 onwards)

- Objective: Launch with initial partner customers, onboard additional clients, and refine the application.

- Key Tasks:

  - Partner onboarding and customer support setup

  - Execution of go-to-market plan

  - Planning for V2 UX/application based on feedback

- Dependencies: Completion of TRL 6 and beta feedback incorporation

- Risks: Market entry challenges; onboarding issues; skilled resources demand.

We have allowed 5 months of contingency given the highly complex nature of AI development projects and to allow staff to take leave.

Risk Register

| Risk | Type | Likelihood | Impact | Mitigation Strategy | Interdependencies |
| --- | --- | --- | --- | --- | --- |
| Data Acquisition Delays | Technical | Medium | High | Formal data-sharing agreements with partners | Essential for TRL 4 dataset preparation |
| Right People Resources Availability | Managerial | Medium | High | Advance hiring strategy and use of external networks | Affects all TRLs and launch phases |
| Model Training Challenges | Technical | High | High | Implement iterative feedback and fallback models | Dependent on TRL 4 data acquisition |
| Significant Issues in Beta Testing | Technical | Medium | High | Allocate extra testing time; proactive issue tracking | Affects TRL 5-6 completion and timeline |
| Legal and Compliance Issues | Legal/Commercial | Medium | High | Engage legal counsel from project start, adhere to Consumer Duty guidelines | Linked to TRL 6 completion |
| Customer Onboarding Delays | Commercial | Medium | Medium | Develop customer support resources in advance | Essential for successful initial launch |
| Environmental Impact | Environmental | Low | Medium | Minimize energy use through cloud-based infrastructure | Not directly interdependent |